## SD-Comment Session
Response of 100% SD comments tracker
Send the MEP (100% SD) comments impacting other disciplines like Arch/STR/ID to PM
Obtain FM comments
Obtain Multi-D comments
Obtain STR comments impacting MEP
Obtain ARCH comments
Obtain LNDS comments
Obtain LS comments
Obtain ID comments
Obtain Baseline program from PM for DD stage
Send the List of dependencies to PM (Refer 100% DD Dependencies Tab)

## SD - Space Planning
Power
Carry out electrical load estimate & compare with the utility allocation for the plot
Indicate the location of substations/LV rooms and indicate all the equipment
Indicate the location of Generator including all the equipment & ELV room
Indicate the location of fuel fill point assembly and indicate connection upto the day tank
Indicate the core electrical room showing all elect panels/trays/busbars/meters
Indicate the major services routing (incoming HV cables, busbars & cable trays to the core elect room)
Air Conditioning
Carry out Cooling load estimate & compare with the utility allocation for the plot
Formulate high level chilled water distribution strategy including no of risers & pumps
Indicate the ETS & pumproom including all the equipment
Indicate the chilled water tie-in connections
Indicate the chilled water pipe routing upto the core
Allocate shaft for chilled water risers within the core
General Ventilation
Carry out General ventilation load estimate
Formulate high level ventilation strategy including no of FAHU's & risers
Indicate the FAHU rooms including all the equipment
Indicate the FA/EA duct routing and allocate shafts within core/apartments
Indicate the louver requirements for FA/EA
Smoke Management
Carry out smoke ventilation estimate
Formulate high level smoke ventilation strategy including no of Fans & risers
Indicate the Fan locations including all the equipment
Indicate the SMA/SEA duct routing and allocate shafts within core
Indicate the louver requirements for SMA/SEA
Parking Ventilation
Carry out Parking ventilation estimate
Formulate high level parking ventilation strategy including no of Fans & risers
Indicate the Fan locations including all the equipment
Indicate the MA/EA duct routing and allocate shafts
Indicate the louver requirements for MA/EA
Potable Water
Carry out Water demand calculation & tank sizing & compare with the utility allocation for the plot
Formulate high level strategy for domestic water system
Indicate the tanks, pump rooms including all the equipment
Indicate the main riser routing from the pumproom to the core
Indicate water meter room & risers within the core area
Drainage
Carry out Drainage calculation & compare with the utility allocation for the plot
Formulate high level strategy for drainage system including the diversions & attic requirements
Carry out drainage pipe sizing calculation
Allocate shafts with the apartments/amenities & core area (for diversions where required)
Connect the risers to tie-in connections and verify the floor to floor height where tie-in connection is made
LPG/SNG
Carry out Gas Demand calculation & compare with the utility allocation for the plot
Formulate high level strategy for GAS system including the diversions & attic requirements
Locate the GAS tank or PRMS room where infra network is available
Allocate shafts with the apartments/F&B's/Restaurants
Indicate routings from PRMS to each shaft
Identify any attic requirement for GAS pipe diversions
Storm Water
Carry out Storm Water Calculation & compare with the utility allocation for the plot, where applicable
Verify if utility connection is available or free discharge
Evaluate the requirement of attenuation tank where utility connection is available
Indicate the attenuation tank & pumps where required
Formulate high level strategy for Storm water system
Indicate the shafts and identify any diversions required
Identify the final discharge point or if any attenuation tank is required
Storm Water
Carry out Fire Pump sizing calculation & tank sizing
Formulate high level strategy for fire fighting system identifying the high zone/low zone connections
Verify the fire pump coverage vertically (90m restriction)
Indicate the fire water tank & pumproom including all the equipment
Indicate the FHC's on all the floors and indicate the risers (core and other areas)
Indicate the FF riser pipe routing from fire pump room to the core risers
Indicate breaching inlets and show connections upto the tank
MEP Coordination - Space Planning
Consolidate all the space on combined layouts and coordinate between M/E/P
Ensure the clear height requirements in all the spaces are met
Share the combined layouts with arch/str for their review and feedback
Issue the coordinated layouts to BIM modellers to start modelling
Model all the electrical spaces including all the electrical equipment
Model all the major electrical containments and busbar routings
Model all HVAC spaces including all the equipment
Model all the major services routing
Model all PHE spaces including all the equipment
Model all the major services routing
Issue the combined MEP mark-ups to arch/STR for review
Multi-D coordination
Obtain feedback from arch/str/landscape/façade on the MEP space planning
Organise coordination meeting to discuss the feedbacks and agree on resolutions
Revise the MEP space planning & repeat the steps within MEP coordination
Issue consolidated space planning layouts to all parties

## SD- STR Coodination
MEP Equipment Plinth/Equipment weights
MEP to provide Equipment plinth location/ Equipment weights
Obtain the updated structure model incorporating MEP Equipment plinths
MEP to review the structure model and highlight any discrepancies in plinth locations to STR
Send confirmation mail to STR
STR Openings | NOT INCLUDED
Elect Distribution Strategy
Obtain the power requirements for VT
Obtain the power requirements for Pool/Spa
Obtain the power requirements for BMU
Obtain the power requirements for white goods from ID
Obtain the power requirement for HVAC equipment inlcuding locations on the model
Obtain the power requirement for PHE equipment inlcuding locations on the model
Engrs to provide mark-up/info for all the small power points
Prepare preliminary load schedules for all SMDB's/ MCC's/MDB's
Prepare overall LV schematics
Prepare FA loop calculations
Prepare overall FA schematics
Carry out EM lighting calcualation for all areas
Carry out CBS calculations
Prepare overall CBS schematics
Engrs to provide indicative containment (including FA/EM ltg) routes to modellers
Modellers to model all the containment routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Modelers to locate all the small power points (sockets, isolators,connection units, etc) - Track floor-wise
Project BIM lead to review the layouts and 3D model - Track floor-wise
Engrs to review the layouts and 3D model - Track floor-wise
HVAC Distribution Strategy
Carry out parking ventilation calculation
Prepare parking ventilation schematics
Engr to provide mark-ups/info to modellers
Modellers to model all the duct routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Carry out chilled water network sizing (PN rating) calculation
Prepare chilled water schematics
Engr to provide mark-ups/info (chilled water system) to modellers
Modellers to model all the chilled water routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Obtain ventilation requirements from pool/spa/water feature plantrooms (if applicable)
Carry out ventilation calculation
Prepare ventilation schematics
Engr to provide mark-ups/info (ventilation) to modellers
Modellers to model all the duct routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Carry out smoke ventilation calculation
Prepare smoke ventilation schematics
Engr to provide mark-ups/info (smoke ventilation) to modellers
Modellers to model all the duct routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
PHE Distribution Strategy
Obtain the drainage requirements from pool/spa/water feature plantrooms (if applicable)
Carry out Drainage (pipe sizing) calculation
Prepare drainage schematics
Engr to provide mark-ups/info to modellers
Modellers to model all the drainage pipe routes in coordination with other disciplines upto tie-in points
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Carry out Rainwater Drainage Calculation
Prepare drainage schematics
Engr to provide mark-ups/info to modellers
Modellers to model all the drainage pipe routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Carry out Domestic water demand calculation
Prepare domestic water schematics
Engr to provide mark-ups/info to modellers
Modellers to model all the water supply pipe routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Carry out Irrigation water demand calculation
Prepare Irrigation water distribution schematics
Engr to provide mark-ups/info to modellers
Modellers to model all the water supply pipe routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Carry out LPG demand calculation
Prepare LPG schematics
Engr to provide mark-ups/info to modellers
Modellers to model all the LPG pipe routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Carry out Fire fighting calculation
Prepare fire fighting system schematics
Engr to provide mark-ups/info to modellers
Modellers to model all the LPG pipe routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
MEP Coordination - STR
Project BIM leads to carry out multi-D coordination for all services modelled
Engrs to validate all the multi-D coordination
BIM Manager to generate the clash report for MEP vs STR
BIM lead and engrs to mark the openings on the model and discuss with Lead engrs
Wall/Floor Openings
Confirm the clear height (ceiling or space below services) requirement for the FOH & BOH area
Obtain latest Wall elevation drawings from STR team
Project BIM leads to transfer the openings from model to CAD file
Engrs to validate the openings
Engrs to send the opening layouts to STR for incorporating in their model
Engrs/BIM Leads to initiate coordination with STR for their feedback
Engrs to provide information to modellers to validate and revise the model based on structural feedback
Engrs to provide updated feedback to STR team
Obtain the updated structure model incorporating MEP openings
BIM Leads & Engrs to review the structure model and highlight any discrepancies to STR
Send confirmation mail to STR
BIM to revise the model based on the final STR agreement
Raft/basement slab coordination
PHE Engr to indicate the location of all sump pits & channel drains
PHE modeller to model the sump pits and channel drains
PHE modeller/engr to coordinate with pile caps and adjust the location of drains and pits
Project BIM lead to review the layouts and 3D model
Engr to review the layouts and 3D model
Elect Engr to prepare Earthing schematics
Engr to provide information to modeller about location & quantity of earth pits
Modeller to model all the earth pits and coordinate with sump pits, drains and pile caps
Project BIM lead to review the layouts and 3D model
Engr to review the earthing layouts and 3D model
Project BIM lead to prepare a consolidated layout indicating Sump pits, drains & earth pits
Engrs to review and share layout with STR team
Calculation validation
Engrs to update AC calculations based on the above coordination
Engrs to update Ventilation calculations based on the above coordination
Engrs to update Smoke Ventilation calculations based on the above coordination
Engrs to update Fire fighting calculations based on the above coordination
Engrs to update Rainwater/Drainage calculations based on the above coordination
Engrs to update Irrigation/domestic water calculations based on the above coordination
Engrs to update EM ltg calculations based on the above coordination
Engrs to update FA calculations based on the above coordination

## SD-ID Coodination
RCP Coordination | NOT INCLUDED
RCP Coordination - 2Bdr Layout
Obtain the ID ceiling layout with air terminal placeholders
SLT to provide RCP with lighting positions
Elect Engr to provide mark-ups for FA system - Check for any CO detectors (kitchen) in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to ID
RCP Coordination - 4Bdr Layout
Obtain the ID ceiling layout with air terminal placeholders
SLT to provide RCP with lighting positions
Elect Engr to provide mark-ups for FA system - Check for any CO detectors (kitchen) in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to ID
RCP Coordination - Main Lobby
Obtain the ID ceiling layout with air terminal placeholders
SLT to provide RCP with lighting positions
Elect Engr to carry out emergency lighting calculation
Elect Engr to provide mark-ups for EM ltg, FA system & motion sensors - Check for any strobes in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model EM ltg, FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to ID
RCP Coordination - Main Lift Lobby
Obtain the ID ceiling layout with air terminal placeholders
SLT to provide RCP with lighting positions
Elect Engr to carry out emergency lighting calculation
Elect Engr to provide mark-ups for EM ltg, FA system & motion sensors - Check for any strobes in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model EM ltg, FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to ID
RCP Coordination - Multipurpose/Resident's Lounge
Obtain the ID ceiling layout with air terminal placeholders
SLT to provide RCP with lighting positions
Elect Engr to carry out emergency lighting calculation
Elect Engr to provide mark-ups for EM ltg, FA system & motion sensors - Check for any strobes in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model EM ltg, FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to ID
RCP Coordination - Multipurpose/Resident's Lounge
Obtain the ID ceiling layout with air terminal placeholders
SLT to provide RCP with lighting positions
Elect Engr to carry out emergency lighting calculation
Elect Engr to provide mark-ups for EM ltg, FA system & motion sensors - Check for any strobes in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model EM ltg, FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to ID
RCP Coordination - Library/Co-working space
Obtain the ID ceiling layout with air terminal placeholders
SLT to provide RCP with lighting positions
Elect Engr to carry out emergency lighting calculation
Elect Engr to provide mark-ups for EM ltg, FA system & motion sensors - Check for any strobes in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model EM ltg, FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to ID
RCP Coordination - Gym
Obtain the ID ceiling layout with air terminal placeholders
SLT to provide RCP with lighting positions
Elect Engr to carry out emergency lighting calculation
Elect Engr to provide mark-ups for EM ltg, FA system & motion sensors - Check for any strobes in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model EM ltg, FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to ID
RCP Coordination - Apartment Corridor (Select the floor having any diversions)
Obtain the ID ceiling layout with air terminal placeholders
SLT to provide RCP with lighting positions
Elect Engr to carry out emergency lighting calculation
Elect Engr to provide mark-ups for EM ltg, FA system & motion sensors - Check for any strobes in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model EM ltg, FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to ID
RCP Coordination - Kids Play Area
Obtain the ID ceiling layout with air terminal placeholders
SLT to provide RCP with lighting positions
Elect Engr to carry out emergency lighting calculation
Elect Engr to provide mark-ups for EM ltg, FA system & motion sensors - Check for any strobes in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model EM ltg, FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to ID
RCP Coordination - Cinema
Obtain the ID ceiling layout with air terminal placeholders
SLT to provide RCP with lighting positions
Elect Engr to carry out emergency lighting calculation
Elect Engr to provide mark-ups for EM ltg, FA system & motion sensors - Check for any strobes in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model EM ltg, FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to ID
RCP Coordination - Spa
Obtain the ID ceiling layout with air terminal placeholders
SLT to provide RCP with lighting positions
Elect Engr to carry out emergency lighting calculation
Elect Engr to provide mark-ups for EM ltg, FA system & motion sensors - Check for any strobes in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model EM ltg, FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to ID
RCP Coordination - Changing Room
Obtain the ID ceiling layout with air terminal placeholders
SLT to provide RCP with lighting positions
Elect Engr to carry out emergency lighting calculation
Elect Engr to provide mark-ups for EM ltg, FA system & motion sensors - Check for any strobes in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model EM ltg, FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to ID

## SD-BOH Area RCP
BOH Areas - RCP Coordination (Repeat these steps for each floor)
Obtain the ID ceiling layout with air terminal placeholders
Elect Engr to carry out lighting calculation for all BOH areas
Elect Engr to check the lighting control strategy against concept report/brand guidelines and provide mark-up/info for motion sensors
Elect modeler to model ltg, motion detectors and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
Elect modeler to update the model based on the comments above
Elect BIM lead to provide RCP with lighting & sensor positions
Elect Engr to carry out emergency lighting calculation
Elect Engr to provide mark-ups for EM ltg, FA system & motion sensors - Check for any strobes in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model EM ltg, FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to Arch
Calculation validation
Engrs to update AC calculations based on the above coordination
Engrs to update Ventilation calculations based on the above coordination
Engrs to update Smoke Ventilation calculations based on the above coordination
Engrs to update Fire fighting calculations based on the above coordination
Engrs to update Rainwater/Drainage calculations based on the above coordination
Engrs to update Irrigation/domestic water calculations based on the above coordination
Engrs to update EM ltg calculations based on the above coordination
Engrs to update FA calculations based on the above coordination

## SD-Submission
100% SD Report
Identify any risks based on the progress during SD and append to the report
Engrs to update the latest bulk loads/equipment in the report
Engrs to update any strategies as applicable in the report
Issue the report to QA/QC team
Obtain QA/QC comments
Update the report based on QA/QC comments
Lead engr to review all the calculations
Engrs to update and upload all the calculations to ACC submission folder
100% SD Calculations
Engrs to update all the calculations based on the above coordination
Lead engr to review all the calculations
Update the calculations based on review
Issue the calculations to QA/QC team
Obtain QA/QC comments
Update the calculations based on QA/QC comments
Lead engr to review all the calculations
Engrs to update and upload all the calculations to ACC submission folder
100% SD Schematics
Engrs to review and comment on all the schematics based on the above coordination & calculations
Modellers to update the schematics
Engrs to review the updated schematics
Lead engrs to review all the schematics
Update the schematics based on the review
Issue the schematics to QA/QC team
Obtain QA/QC comments
Update the calculations based on QA/QC comments
Modellers to update the model based on the comments, carry out interference check
BIM leads to verify all the comments are incorporated
Repeat the above steps until all the comments are closed
BIM leads to verify the final layouts and upload on the ACC submission folder
100% SD Layouts
Project BIM leads to verify all the layouts against TIDP
Project BIM leads to review the models & layouts and share it with BIM manager for further review
BIM leads / Modelers to share all the layouts with Engrs for review
Engrs to review all the layouts and provide comments
Modellers to update the model based on the comments, carry out interference check
BIM leads to verify all the comments are incorporated
Repeat the above steps until all the comments are closed
Modelers to share the final layouts with Engrs
Engrs to share the final layouts with MLD for QA/QC
Engrs to validate the comments from MLD, discuss with MLD QA/QC team and agree on the way forward
Engrs to provide the mark-up/information to the modelers to update the models
Modellers to update the model based on the comments, carry out interference check
BIM leads to verify all the comments are incorporated
Repeat the above steps until all the comments are closed
BIM leads to verify the final layouts and upload on the ACC submission folder