## WBS
Space Planning | Carry out electrical load estimate & compare with the concept report
Indicate the location of substations / LV rooms
Indicate the major services routing
STR Coordination | MEP equipment plinths / equipment weights
Provide equipment plinth locations to STR
Review the structure model and highlight clashes
ID - RCP Coordination | Electrical distribution strategy
Obtain the power requirements for VT
Prepare the overall LV schematics
BoH Area RCP Coordination | BoH RCP coordination
Coordinate the ceiling services in the BoH areas
Issue the coordinated RCP layouts
Submission | Design submission
Compile the drawings and calculations
Issue the submission package