## Sheet4
BOH Areas - RCP Coordination (Repeat these steps for each floor)
Obtain the ID ceiling layout with air terminal placeholders
Elect Engr to carry out lighting calculation for all BOH areas
Elect Engr to check the lighting control strategy against concept report/brand guidelines and provide mark-up/info for motion sensors
Elect modeler to model ltg, motion detectors and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
Elect modeler to update the model based on the comments above
Elect BIM lead to provide RCP with lighting & sensor positions
Elect Engr to carry out emergency lighting calculation
Elect Engr to provide mark-ups for EM ltg, FA system & motion sensors - Check for any strobes in the brand guidelines
Elect Engr to provide mark-ups for access panels (for any devices within the ceiling void)
Elect modeler to model EM ltg, FA devices & access panels and coordinate with other disciplines
Elect BIM lead to review the model
Elect Engr to review the layouts
PHE Engr to carry out hot water sizing & circulation pump (where applicable) sizing calculation
PHE Engr to provide mark-ups for Sprinklers & access panels for any services above false celing - Check sprinkler types in the brand guidelines
PHE modeler to model all sprinklers & piping and coordinate with other disciplines
PHE BIM lead to review the model
PHE Engr to review the layouts
HVAC Engr to provide mark-ups for AC terminals & access panels - Check brand guidelines for the locations of FCU's, any other requirements
HVAC modeler to model all the air terminals, FCU's & duct routing and coordinate with other disciplines
HVAC BIM lead to review the model
HVAC Engr to review the layouts
BIM Leads to review the model and clear any clashes
Engrs to review and validate the coordinated RCP
Any comments to be addressed by the modelers
Engrs to share the final coordinated RCP to Arch
Calculation validation
Engrs to update AC calculations based on the above coordination
Engrs to update Ventilation calculations based on the above coordination
Engrs to update Smoke Ventilation calculations based on the above coordination
Engrs to update Fire fighting calculations based on the above coordination
Engrs to update Rainwater/Drainage calculations based on the above coordination
Engrs to update Irrigation/domestic water calculations based on the above coordination
Engrs to update EM ltg calculations based on the above coordination
Engrs to update FA calculations based on the above coordination