## Sheet3
MEP Equipment Plinth/Equipment weights
MEP to provide Equipment plinth location/ Equipment weights
Obtain the updated structure model incorporating MEP Equipment plinths
MEP to review the structure model and highlight any discrepancies in plinth locations to STR
Send confirmation mail to STR
Core Wall Openings
Confirm the clear height (ceiling or space below services) requirement for the FOH & BOH area
Elect Distribution Strategy
Obtain the power requirements for VT
Obtain the power requirements for Pool/Spa
Obtain the power requirements for BMU
Obtain the power requirements for white goods from ID
Obtain the power requirement for HVAC equipment inlcuding locations on the model
Obtain the power requirement for PHE equipment inlcuding locations on the model
Engrs to provide mark-up/info for all the small power points
Prepare preliminary load schedules for all SMDB's/ MCC's/MDB's
Prepare overall LV schematics
Prepare FA loop calculations
Prepare overall FA schematics
Carry out EM lighting calcualation for all areas
Carry out CBS calculations
Prepare overall CBS schematics
Engrs to provide indicative containment (including FA/EM ltg) routes to modellers
Modellers to model all the containment routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Modelers to locate all the small power points (sockets, isolators,connection units, etc) - Track floor-wise
Project BIM lead to review the layouts and 3D model - Track floor-wise
Engrs to review the layouts and 3D model - Track floor-wise
HVAC Distribution Strategy
Carry out parking ventilation calculation
Prepare parking ventilation schematics
Engr to provide mark-ups/info to modellers
Modellers to model all the duct routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Carry out chilled water network sizing (PN rating) calculation
Prepare chilled water schematics
Engr to provide mark-ups/info (chilled water system) to modellers
Modellers to model all the chilled water routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Obtain ventilation requirements from pool/spa/water feature plantrooms (if applicable)
Carry out ventilation calculation
Prepare ventilation schematics
Engr to provide mark-ups/info (ventilation) to modellers
Modellers to model all the duct routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Carry out smoke ventilation calculation
Prepare smoke ventilation schematics
Engr to provide mark-ups/info (smoke ventilation) to modellers
Modellers to model all the duct routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
PHE Distribution Strategy
Obtain the drainage requirements from pool/spa/water feature plantrooms (if applicable)
Carry out Drainage (pipe sizing) calculation
Prepare drainage schematics
Engr to provide mark-ups/info to modellers
Modellers to model all the drainage pipe routes in coordination with other disciplines upto tie-in points
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Carry out Rainwater Drainage Calculation
Prepare drainage schematics
Engr to provide mark-ups/info to modellers
Modellers to model all the drainage pipe routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Carry out Domestic water demand calculation
Prepare domestic water schematics
Engr to provide mark-ups/info to modellers
Modellers to model all the water supply pipe routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Carry out Irrigation water demand calculation
Prepare Irrigation water distribution schematics
Engr to provide mark-ups/info to modellers
Modellers to model all the water supply pipe routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Carry out LPG demand calculation
Prepare LPG schematics
Engr to provide mark-ups/info to modellers
Modellers to model all the LPG pipe routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
Carry out Fire fighting calculation
Prepare fire fighting system schematics
Engr to provide mark-ups/info to modellers
Modellers to model all the LPG pipe routes in coordination with other disciplines
Project BIM lead to review the layouts and 3D model
Engrs to review the layouts and 3D model
MEP Coordination
Project BIM leads to carry out multi-D coordination for all services modelled
Engrs to validate all the multi-D coordination
BIM Manager to generate the clash report for MEP vs STR
BIM lead and engrs to mark the openings on the model and discuss with Lead engrs
Wall/Floor Openings
Obtain latest Wall elevation drawings from STR team
Project BIM leads to transfer the openings from model to CAD file
Engrs to validate the openings
Engrs to send the opening layouts to STR for incorporating in their model
Engrs/BIM Leads to initiate coordination with STR for their feedback
Engrs to provide information to modellers to validate and revise the model based on structural feedback
Engrs to provide updated feedback to STR team
Obtain the updated structure model incorporating MEP openings
BIM Leads & Engrs to review the structure model and highlight any discrepancies to STR
Send confirmation mail to STR
BIM to revise the model based on the final STR agreement
Raft/basement slab coordination
PHE Engr to indicate the location of all sump pits & channel drains
PHE modeller to model the sump pits and channel drains
PHE modeller/engr to coordinate with pile caps and adjust the location of drains and pits
Project BIM lead to review the layouts and 3D model
Engr to review the layouts and 3D model
Elect Engr to prepare Earthing schematics
Engr to provide information to modeller about location & quantity of earth pits
Modeller to model all the earth pits and coordinate with sump pits, drains and pile caps
Project BIM lead to review the layouts and 3D model
Engr to review the earthing layouts and 3D model
Project BIM lead to prepare a consolidated layout indicating Sump pits, drains & earth pits
Engrs to review and share layout with STR team
Calculation validation
Engrs to update AC calculations based on the above coordination
Engrs to update Ventilation calculations based on the above coordination
Engrs to update Smoke Ventilation calculations based on the above coordination
Engrs to update Fire fighting calculations based on the above coordination
Engrs to update Rainwater/Drainage calculations based on the above coordination
Engrs to update Irrigation/domestic water calculations based on the above coordination
Engrs to update EM ltg calculations based on the above coordination
Engrs to update FA calculations based on the above coordination