## Sheet5
100% SD Report
Identify any risks based on the progress during SD and append to the report
Engrs to update the latest bulk loads/equipment in the report
Engrs to update any strategies as applicable in the report
Issue the report to QA/QC team
Obtain QA/QC comments
Update the report based on QA/QC comments
Lead engr to review all the calculations
Engrs to update and upload all the calculations to ACC submission folder
100% SD Calculations
Engrs to update all the calculations based on the above coordination
Lead engr to review all the calculations
Update the calculations based on review
Issue the calculations to QA/QC team
Obtain QA/QC comments
Update the calculations based on QA/QC comments
Lead engr to review all the calculations
Engrs to update and upload all the calculations to ACC submission folder
100% SD Schematics
Engrs to review and comment on all the schematics based on the above coordination & calculations
Modellers to update the schematics
Engrs to review the updated schematics
Lead engrs to review all the schematics
Update the schematics based on the review
Issue the schematics to QA/QC team
Obtain QA/QC comments
Update the calculations based on QA/QC comments
Modellers to update the model based on the comments, carry out interference check
BIM leads to verify all the comments are incorporated
Repeat the above steps until all the comments are closed
BIM leads to verify the final layouts and upload on the ACC submission folder
100% SD Layouts
Project BIM leads to verify all the layouts against TIDP
Project BIM leads to review the models & layouts and share it with BIM manager for further review
BIM leads / Modelers to share all the layouts with Engrs for review
Engrs to review all the layouts and provide comments
Modellers to update the model based on the comments, carry out interference check
BIM leads to verify all the comments are incorporated
Repeat the above steps until all the comments are closed
Modelers to share the final layouts with Engrs
Engrs to share the final layouts with MLD for QA/QC
Engrs to validate the comments from MLD, discuss with MLD QA/QC team and agree on the way forward
Engrs to provide the mark-up/information to the modelers to update the models
Modellers to update the model based on the comments, carry out interference check
BIM leads to verify all the comments are incorporated
Repeat the above steps until all the comments are closed
BIM leads to verify the final layouts and upload on the ACC submission folder