## CD - Space Planning
Power
Carry out electrical load estimate & compare with the utility allocation for the plot
Indicate the location of substations/LV rooms and indicate all the equipment
Indicate the location of Generator including all the equipment & ELV room
Indicate the location of fuel fill point assembly and indicate connection upto the day tank
Indicate the core electrical room showing all elect panels/trays/busbars/meters
Indicate the major services routing (incoming HV cables, busbars & cable trays to the core elect room)
Air Conditioning
Carry out Cooling load estimate & compare with the utility allocation for the plot
Formulate high level chilled water distribution strategy including no of risers & pumps
Indicate the ETS & pumproom including all the equipment
Indicate the chilled water tie-in connections
Indicate the chilled water pipe routing upto the core
Allocate shaft for chilled water risers within the core
General Ventilation
Carry out General ventilation load estimate
Formulate high level ventilation strategy including no of FAHU's & risers
Indicate the FAHU rooms including all the equipment
Indicate the FA/EA duct routing and allocate shafts within core/apartments
Indicate the louver requirements for FA/EA
Smoke Management
Carry out smoke ventilation estimate
Formulate high level smoke ventilation strategy including no of Fans & risers
Indicate the Fan locations including all the equipment
Indicate the SMA/SEA duct routing and allocate shafts within core
Indicate the louver requirements for SMA/SEA
Parking Ventilation
Carry out Parking ventilation estimate
Formulate high level parking ventilation strategy including no of Fans & risers
Indicate the Fan locations including all the equipment
Indicate the MA/EA duct routing and allocate shafts
Indicate the louver requirements for MA/EA
Potable Water
Carry out Water demand calculation & tank sizing & compare with the utility allocation for the plot
Formulate high level strategy for domestic water system
Indicate the tanks, pump rooms including all the equipment
Indicate the main riser routing from the pumproom to the core
Indicate water meter room & risers within the core area
Drainage
Carry out Drainage calculation & compare with the utility allocation for the plot
Formulate high level strategy for drainage system including the diversions & attic requirements
Carry out drainage pipe sizing calculation
Allocate shafts with the apartments/amenities & core area (for diversions where required)
Connect the risers to tie-in connections and verify the floor to floor height where tie-in connection is made
LPG/SNG
Carry out Gas Demand calculation & compare with the utility allocation for the plot
Formulate high level strategy for GAS system including the diversions & attic requirements
Locate the GAS tank or PRMS room where infra network is available
Allocate shafts with the apartments/F&B's/Restaurants
Indicate routings from PRMS to each shaft
Identify any attic requirement for GAS pipe diversions
Storm Water
Carry out Storm Water Calculation & compare with the utility allocation for the plot, where applicable
Verify if utility connection is available or free discharge
Evaluate the requirement of attenuation tank where utility connection is available
Indicate the attenuation tank & pumps where required
Formulate high level strategy for Storm water system
Indicate the shafts and identify any diversions required
Identify the final discharge point or if any attenuation tank is required
Storm Water
Carry out Fire Pump sizing calculation & tank sizing
Formulate high level strategy for fire fighting system identifying the high zone/low zone connections
Verify the fire pump coverage vertically (90m restriction)
Indicate the fire water tank & pumproom including all the equipment
Indicate the FHC's on all the floors and indicate the risers (core and other areas)
Indicate the FF riser pipe routing from fire pump room to the core risers
Indicate breaching inlets and show connections upto the tank
MEP Coordination - Space Planning
Consolidate all the space on combined layouts and coordinate between M/E/P
Ensure the clear height requirements in all the spaces are met
Share the combined layouts with arch/str for their review and feedback
Issue the coordinated layouts to BIM modellers to start modelling
Model all the electrical spaces including all the electrical equipment
Model all the major electrical containments and busbar routings
Model all HVAC spaces including all the equipment
Model all the major services routing
Model all PHE spaces including all the equipment
Model all the major services routing
Issue the combined MEP mark-ups to arch/STR for review
Multi-D coordination
Obtain feedback from arch/str/landscape/façade on the MEP space planning
Organise coordination meeting to discuss the feedbacks and agree on resolutions
Revise the MEP space planning & repeat the steps within MEP coordination
Issue consolidated space planning layouts to all parties

## CD-Submission
100% CD Report
Identify any risks based on the progress during CD and append to the report
Engrs to update the latest bulk loads/equipment in the report
Engrs to update any strategies as applicable in the report
Issue the report to QA/QC team
Obtain QA/QC comments
Update the report based on QA/QC comments
Lead engr to review all the calculations
Engrs to update and upload all the calculations to ACC submission folder
100% CD Calculations
Engrs to update all the calculations based on the above coordination
Lead engr to review all the calculations
Update the calculations based on review
Issue the calculations to QA/QC team
Obtain QA/QC comments
Update the calculations based on QA/QC comments
Lead engr to review all the calculations
Engrs to update and upload all the calculations to ACC submission folder
100% CD Schematics
Engrs to review and comment on all the schematics based on the above coordination & calculations
Modellers to update the schematics
Engrs to review the updated schematics
Lead engrs to review all the schematics
Update the schematics based on the review
Issue the schematics to QA/QC team
Obtain QA/QC comments
Update the calculations based on QA/QC comments
Modellers to update the model based on the comments, carry out interference check
BIM leads to verify all the comments are incorporated
Repeat the above steps until all the comments are closed
BIM leads to verify the final layouts and upload on the ACC submission folder
100% CD Layouts
Project BIM leads to verify all the layouts against TIDP
Project BIM leads to review the models & layouts and share it with BIM manager for further review
BIM leads / Modelers to share all the layouts with Engrs for review
Engrs to review all the layouts and provide comments
Modellers to update the model based on the comments, carry out interference check
BIM leads to verify all the comments are incorporated
Repeat the above steps until all the comments are closed
Modelers to share the final layouts with Engrs
Engrs to share the final layouts with MLD for QA/QC
Engrs to validate the comments from MLD, discuss with MLD QA/QC team and agree on the way forward
Engrs to provide the mark-up/information to the modelers to update the models
Modellers to update the model based on the comments, carry out interference check
BIM leads to verify all the comments are incorporated
Repeat the above steps until all the comments are closed
BIM leads to verify the final layouts and upload on the ACC submission folder